# The plan for Quality Development in our school, Portugal – 15 – 20 May 2016, Mgr. Jozef Sopoliga

My outcomes of the course are these:

# Plan how to make a plan of improvement:

1. Implement the mission of the school in the school reality:
	1. Analyse and update mission statement with all teachers in our school
	2. Update SWOT of the school with all teachers
	3. Make an action plan how to set specific goals for each area of our school education with reflection of the school mission
	4. Indicators:
		1. EFQM awareness of teachers
		2. Updated school year plan
		3. Updated school curriculum in all stages of education
		4. Tools to monitor implementation how are goals are fulfilled
2. Improve results and behaviour in the middle school
	1. Analyse student’s results
	2. Analyse student’s behaviour
	3. Make a plan of improvement results and behaviour in the middle school
	4. Indicators: Plan which would consists
		1. how to change of teaching instruction
		2. New trainings for teachers
		3. Budget
		4. Tools to monitor results

Analysis made by September 2016

Start: September 2016

End: August 2017

# Make thinking valued, visible, actively promoted

**Goal:** Make thinking valued, visible, actively promoted in 2nd year of high school physics in 2016/2017 school year and next year deploy it in all grades stages of education in the school

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Action** | **Responsible** | **Involved** |  **Due to**  | **Indicators** |
| Read the book: R. Ritchhart: Creating Culture of thinking… | Jozef |  | End of June 2016 | Documents with necessary Instruments ready to implement in the 2nd year of high school physics |
| Rewrite physics teaching plan for 2nd year of physics  | Jozef | Other teacherss | 20 August 2016 | New teaching plan with instruments/activities necessary for deploying project |
| Promotion of new project among teacher | Jozef |  | End of February 2017 | Presentations, open lessons for other teachers to observe/video for teachers, discussion and analysis of it |
| Training for teachers who are willing to volunteer + 1st teachers try | Jozef |  | End of June 2017 | Presentations, open lesson/video for teachers |
| Presentation of outcomes | Jozef and  | other teachers who are willing to volunteer | End of June 2017 | Presentation of activities and outcomes to teachers and to public |
| Start of 2nd phase of the project | Jozef and other teachers | other teacher who are willing to volunteer | Beginning of September 2017 | New plan for the 2nd phase |

Make more teachers (physics teachers) more involved since the beginning.